## Foglio1
|  | Nov |  | Dic |  |  |  | Gen
WHAT | WHO | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2
Modifications DB (notification and activities and travels) | Matteo
Login + errors | Matteo
Registration + errors | Matteo
Update/add Ranged Pref+ errors | Emilio
Delete Ranged Pref+ errors | Emilio
Update Boolean Pref+ errors | Emilio
Get Preferences | Emilio
Add Activity+ errors | Matteo
Overlapping Algorithm | Matteo
BestTravelAlgorithm | Matteo
Need Notification Algorithm | Matteo
Delete Activity+ errors | Mattia
Update Activity+ errors | Mattia
Get Calendar | Mattia
Add tag+ errors | Matteo
Delete tag+ errors | Matteo
Notification retrieval | Mattia | bar: Nov 5
Compute best travel mean | Matteo
Desktop Client | Matteo | bar: Nov 5
Mobile Client (Android) | Emilio | bar: Nov 5 to Dic 2
Mobile Client (Android) | Mattia | bar: Nov 5 to Dic 2
Desktop Client Day Overview | Matteo | bar: Dic 1
Testing | Matteo | bar: Dic 2 to Dic 3